## Task Duration Charts
Marketing Critical Tasks and Phases |  |  | Updates Critical Tasks and Phases
Start Date | End Date | Task | Start Date | End Date | Task
2020-04-20 | 2020-04-24 | Review and Source marketing platforms | 2020-04-20 | 2020-04-24 | Gather grouped feedback units
2020-04-20 | 2020-06-22 | Implement marketing | 2020-04-20 | 2020-06-22 | Determine which updates to address first
2020-04-20 | 2020-05-20 | Review metrics for sales | 2020-04-20 | 2020-05-20 | Develop update
2020-05-20 | 2020-05-22 | Determine value of current marketing strategy | 2020-05-20 | 2020-05-22 | Test update for compatability
2020-05-25 | 2020-05-29 | Update marketing platform | 2020-05-25 | 2020-05-29 | Distribute update
2020-06-01 | 2020-06-22 | Diversify marketing strategy | 2020-06-01 | 2020-06-22 | Review update feedback
Marketing Tasks and Duration |  |  | Update Tasks and Duration
Critical Tasks |  | Task Duration in days | Critical Tasks |  | Task Duration in days
Source marketing platforms | 0 | 4 | Gather grouped feedback units | 0 | 4
Implement marketing | 0 | 63 | Determine which updates to address first | 0 | 63
Review metrics for sales | 0 | 30 | Develop update | 0 | 30
Determine value of current marketing strategy | 30 | 2 | Test update for compatability | 30 | 2
Update marketing platform | 35 | 4 | Distribute update | 35 | 4
Diversify marketing strategy | 42 | 21 | Review update feedback | 42 | 21

## Market and Update Schedules
Marketing and Update Weekly Schedule Overview
Week of
| 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22
Tasks/ Milestones
Marketing
Review and Source marketing platforms | bar: 2020-04-20
Implement marketing
Review metrics for sales | bar: 2020-04-20 to 2020-05-18
Determine value of current marketing strategy | bar: 2020-05-18 to 2020-05-25
Update marketing platform | bar: 2020-05-25 to 2020-06-01
Diversify marketing strategy | bar: 2020-06-01 to 2020-06-22
Updates
Gather grouped feedback units | bar: 2020-04-20
Determine which updates to address first
Develop update | bar: 2020-04-20 to 2020-05-18
Test update for compatability | bar: 2020-05-18 to 2020-05-25
Distribute update | bar: 2020-05-25 to 2020-06-01
Review update feedback | bar: 2020-06-01 to 2020-06-22